## Sheet1
Project Supplies
Order # | Cost | Description | Date Submitted | Revision Date (?) | Date Approved | Received | Notes
1 | 108.85 | Wave LoRa Modules x 6 | 2024-09-16 | 2024-09-17 | 2024-09-17
2 | 22.15 | Jumpers and Justin's hogs x 2 | 2024-09-23 | n/a | 2024-09-23
3 | 210.075 | Petal v0.0 hardware order | 2024-10-14 | 2024-10-15 | 2024-10-15 | Friday,Octoder 18, 2024 | 47uF caps and 1k5 res were out of stock @ mouser, switched to kyocera caps and found res in stock on digikey
4 | 61.07 | Spare petal hardware and sd cards. Mouser + Amazon | 2024-11-04 | n/a | 2024-11-05 | Friday, October 8 and Tuesday October 12 | Amazon order came later than mouser
5 | 21.37 | IPEX to N and N to SMA RF connectors | 2024-11-11 | n/a | 2024-11-13 |  | Delayed… pushed back testing a week
n/a
n/a
n/a
PCB
Order # | Estimated Cost | Description | Date Submitted | Revision Date (?) | Date Approved | Notes
1 | 50 | Petal Radio v0.0 x 5 | 2024-10-14 | n/a | 2024-10-15 | JLC was unsure about the footprints for J8 and J7 because of the large solder mask opening. Told them to continue per the gerber -AH
n/a
n/a
n/a
n/a
n/a
n/a
n/a